## Plan
	Total hours to use:	610		Team
	Estimated hours needed:	375,5		Madeleine
	Start date (Plan):	27.04.23		Rajesh
	End date:	06.07.23		Teja
				Jannis
				Manu
				Atif

	Note: Presenting in the lecture doesn’t count into hours
	Note: Preparing the Presentation includes updating the hours sheet
	Note: Duration shows total hours. So if a Meeting is 1.5 hours and 6 people attend it that’s 9 hours total. If a task has 15 hours with 3 workers everyone works 5 hours.

Number	Task	Status	Assigned to	Deadline	Duration	Dependencies

	Teammeetings				90
	Meeting 1	Complete	everyone	20.04.23	9
	Meeting 2	Complete	everyone	27.04.23	9
	Meeting 3	Complete	everyone	04.05.23	9
	Meeting 4	Complete	everyone	11.05.23	9
	Meeting 5	Complete	everyone	25.05.23	9
	Meeting 6	Not Started	everyone	01.06.23	9
	Meeting 7	Not Started	everyone	08.06.23	9
	Meeting 8	Not Started	everyone	15.06.23	9
	Meeting 9	Not Started	everyone	22.06.23	9
	Meeting 10	Not Started	everyone	29.06.23	9

0.	Team			20.04.23	20,5
0.1	Get into Contact (Discord, Github)	Complete	everyone	20.04.23	1,5
0.2	General Planning Project	Complete	Madeleine	14.04.23	3
0.3	General Planning Goals	Complete	Madeleine	14.04.23	1
0.4	Review of Plans	Complete	everyone	18.04.23	5	0.1, 0.2, 0.3, 0.5
0.5	Research Roles	Complete	everyone	20.04.23	5
0.6	Prepare Presentation	Complete	Madeleine	19.04.23	5	0.4

1.	Project Plan			27.04.23	23,5
1.1	Write down work hours	Complete	everyone	27.04.23	1,5
1.2	Draft Project Plan	Complete	Madeleine	22.04.23	6	1
1.3	Review Project Plan	Complete	everyone	24.04.23	6	1.2
1.4	Ready Hours Excel Sheet	Complete	Rajesh, Madeleine	27.04.23	3
1.5	Document Results	Complete	Jannis	27.04.23	2	1
1.6	Prepare Presentation	Complete	Madeleine	26.04.23	5	1.3
1.7	Presentation	Complete	Madeleine	27.04.23	0	1.6

2	Conceptual Model			04.05.23	32,5
2.1	Research Petrinets on Intersections	Complete	Teja, Atif, Manu	23.04.23	3	1
2.2	Logic Road Signs	Complete	Madeleine	22.04.23	1,5	1
2.3	Draft Petrinet	Complete	Teja, Atif, Manu, Madeleine, Jannis	27.04.23	15	2.2, 2.1
2.4	Discussion Petrinet	Complete	everyone	27.04.23	3	2.3
2.5	Verify Petrinet	Complete	Madeleine, Jannis	03.04.23	3	2.4
2.6	Document Results	Complete	Jannis, Rajesh	04.05.23	2	2
2.7	Prepare Presentation	Complete	Teja	03.05.23	5	2.5, 4.3
2.8	Presentation	Complete	Teja	04.05.23	0	2.7

3	Data Analysis			25.05.23	50
3.1	Sheet for Data Collection	Complete	Atif	05.05.23	2	5.3, 6.2
3.2	Research qq Plot, find Reverse Exponential Distribution	Complete	Jannis	27.04.23	2
3.3	Decide on Correct Time for Data Collection	Complete	Atif	05.05.23	1	5.2, 2
3.4	Collect Data (1)	Complete	Atif, Rajesh, Manu, Teja	07.05.23	9	3.1
3.5	Collect Data (2)	Complete	Atif, Rajesh, Manu, Teja	13.05.23	9	3.1
3.6	Collect Data (3)	Complete	Atif, Rajesh, Manu, Teja	13.05.23	9	3.1
3.7	Digitalize Data	Complete	Madeleine, Jannis	14.05.23	6	3.4, 3.5, 3.6
3.8	Histogramm, qq Plot, Chi Square	Complete	Madeleine	15.05.23	5	3.7
3.9	Document Results	Complete	Madeleine	25.05.23	2	3
3.10	Prepare Presentation	Complete	Rajesh	24.05.23	5	3.8
3.11	Presentation	Complete	Rajesh	25.05.23	0	3.10

4	Simulation Programm			01.06.23	67
4.1	Research how traffic is done in Anylogic	Complete	Jannis	20.06.23	2
4.2	Brainstorm Ideas how to Implement Details	Complete	Jannis	27.04.23	3
4.3	Decide on Events and Pallet Elements	Complete	Madeleine, Jannis, Teja	10.04.23	6	4.1, 4.2, 2.5
4.4	Model Current Node	Complete	Jannis	24.05.23	15	2
4.5	Model Roundabout	Complete	Teja,Manu	01.06.23	15	2
4.6	Model Two-Way-Street Variations	Complete	Teja, Manu	01.06.23	15	2
4.7	Insert Data	Complete	Jannis, Teja, Manu	25.05.23	4	3
4.8	Document Results	Complete	Madeleine	28.05.23	2	4
4.9	Prepare Presentation	Complete	Jannis	31.05.23	5	4.7
4.10	Presentation	Complete	Jannis	01.06.23	0	4.9

5	Validation			15.06.23	30
5.1	Brainstorm Ideas	Complete	Atif	27.04.23	2	1
5.2	Review Given Data	Complete	Atif	27.04.23	3	1
5.3	Decide on Data to Measure for Validation	Complete	everyone	27.04.23	3	5.1, 5.2
5.4	Write and Run Experiments for Validation	Complete	Atif	08.06.23	15	4, 5.3
5.5	Document Results	In Progress	Madeleine	14.06.23	2	5.
5.6	Prepare Presentation	In Progress	Atif	14.06.23	5	5.4
5.7	Presentation	Not Started	Atif	15.06.23	0	5.6

6	Experiments			29.06.23	47
6.1	Research ANOVA	Complete	Madeleine	04.05.23	3
6.2	Final Decision on Experiments	Complete	everyone	04.05.23	3	6.1, 5.2
6.3	Write and Run Experiment 1	In Progress	Manu, Teja, Rajesh	20.06.23	7	6.2, 4
6.4	Write and Run Experiment 2	In Progress	Manu, Teja, Rajesh	20.06.23	7	6.2, 4
6.5	Write and Run Experiment 3	In Progress	Manu, Teja, Rajesh	20.06.23	7	6.2, 4
6.6	Write and Run Experiment 4	In Progress	Manu, Teja, Rajesh	20.06.23	7	6.2, 4
6.7	Analyse and Visualize Results	Not Started	Jannis	25.06.23	6	6.3, 6.4, 6.5, 6.6
6.8	Document Results	Not Started	Madeleine	01.07.23	2	6
6.9	Prepare Presentation	Not Started	Manu	28.06.23	5	6.7
6.10	Presentation	Not Started	Manu	29.06.23	0	6.9

7	Final Report			06.07.23	15
7.1	Final Version Documentation	In Progress	Madeleine	05.07.23	6	6
7.2	Print Documentation	Not Started	Madeleine	06.07.23	1	7.1
7.3	Prepare Presentation	Not Started	Madeleine	05.07.23	8	6
7.4	Presentation	Not Started	Madeleine	06.07.23	0	7.3

## Work Packets
				375,5

Start	End	Task	Assigned to	Madeleine	Rajesh	Teja	Atif	Jannis	Manu
13.04.23	20.04.23
	x	Get into Contact (Discord, Github)	everyone	0,25	0,25	0,25	0,25	0,25	0,25	1,5
	x	General Plannung Project	Madeleine	3					3
	x	General Planning Goals	Madeleine	1					1
	x	Review of Plans	everyone		1	1	1	1	1	5
	x	Research Roles	everyone		1	1	1	1	1	5
	x	Prepare Presentation	Madeleine	5					5
	x	Research how traffic is done in Anylogic	Jannis					2		2
		Sum		9,25	2,25	2,25	2,25	4,25	2,25	22,5

Milestone 1 „Team“ (20.04.23)

Start	End	Task	Assigned to	Madeleine	Rajesh	Teja	Atif	Jannis	Manu
20.04.23	27.04.23
	x	Write down work hours	everyone	0,25	0,25	0,25	0,25	0,25	0,25	1,5
	x	Draft Project Plan	Madeleine	6					6
	x	Review Project Plan	everyone	1	1	1	1	1	1	6
	x	Ready Hours Excel Sheet	Rajesh, Madeleine	1,5	1,5					3
	x	Document Results	Jannis					2		2
	x	Prepare Presentation	Madeleine	5					5
	x	Research Petrinets on Intersections	Teja, Atif, Manu			2	2		2	6
	x	Logic Road Signs	Madeleine	1,5					1,5
	x	Draft Petrinet	Teja, Atif, Manu			5	5		5	15
	x	Research qq Plot, find Reverse Exponential Distribution	Rajesh, Jannis		1			1		2
	x	Brainstorm Ideas how to Implement Details	Jannis					3		3
	x	Brainstorm Ideas	Atif				2			2
	x	Review Given Data	Atif				3			3
	x	Discussion Petrinet	everyone	0,5	0,5	0,5	0,5	0,5	0,5	3
		Sum		15,75	4,25	8,75	13,75	7,75	8,75	59

Milestone 2 „Project Plan“ (27.04.23)

Start	End	Task	Assigned to	Madeleine	Rajesh	Teja	Atif	Jannis	Manu
27.04.24	04.05.23
	x	Verify Petrinet	Madeleine, Jannis	1,5				1,5		3
	x	Document Results	Rajesh, Jannis		1			1		2
	x	Prepare Presentation	Teja			5				5
	x	Sheet for Data Collection	Atif				2			2
	x	Decide on Correct Time for Data Collection	Atif				1			1
	x	Decide on Events and Pallet Elements	Manu, Jannis					3	3	6
	x	Research ANOVA	Madeleine	3					3
	x	Final Decision on Experiments	everyone	0,5	0,5	0,5	0,5	0,5	0,5	3
	x	Decide on Data to Measure for Validatioon		0,5	0,5	0,5	0,5	0,5	0,5	3
		Sum		5,5	2	6	4	6,5	4	28

Milestone 3 „Conceptual Model“ (04.05.23)

Start	End	Task	Assigned to	Madeleine	Rajesh	Teja	Atif	Jannis	Manu
04.05.23	11.05.23
	x	Collect Data (1)	Rajesh, Teja, Manu		3	3			3	9
	x	Collect Data (2)	Atif, Jannis, Rajesh		3		3	3		9
	x	Digitalize Data	Madeleine	2					2
		Sum		2	6	3	3	3	3	20

11.05.23	18.05.23
	x	Collect Data (3)	Manu, Rajesh, Teja		3	3			3	9
	x	Digitalize Data	Teja, Rajesh		2	2				4
	x	Histogramm, qq Plot, Chi Square	Madeleine	5					5
	x	Document Results	Madeleine, Jannis	1				1		2
	x	Model Current Node (1)	Jannis					5		5
	x	Model Roundabout (1)	Atif			5				5
		Sum		6	5	5	0	6	3	30

18.05.23	25.05.23
	x	Prepare Presentation	Rajesh		5					5
	x	Model Current Node (2)	Jannis, Madeleine	5				5		10
		Model Roundabout (2)	Atif, Manu				5		5	10
	x	Model Two-Way-Street Variations (1)	Teja			5				5
		Sum		5	5	5	5	5	5	30

Milestone 4 „Data Analysis“ (25.05.23)

Start	End	Task	Assigned to	Madeleine	Rajesh	Teja	Atif	Jannis	Manu
25.05.23	01.06.23
		Model Two-Way-Street Variations (2)	Teja, Rajesh		5	5				10
	x	Insert Data	Atif, Manu				2		2	4
		Document Results	Madeleine	2					2
	x	Prepare Presentation	Jannis					5		5
		Sum		2	5	5	2	5	2	21

Milestone 5 „Simulation Program“ (01.06.23)

Start	End	Task	Assigned to	Madeleine	Rajesh	Teja	Atif	Jannis	Manu
01.06.23	08.06.23
		Write and Run Experiments for Validation	Jannis, Manu, Rajesh		5			5	5	15
		Document Results	Teja			2				2
		Prepare Presentation	Atif				5			5
		Write and Run Experiment 1	Madeleine, Teja	3,5		3,5				7
		Sum		3,5	5	5,5	5	5	5	29

08.06.23	15.06.23
		Write and Run Experiment 2	Teja, Manu			3,5			3,5	7
		Write and Run Experiment 3	Rajesh, Atif		3,5		3,5			7
		Write and Run Experiment 4	Madeleine, Jannis	3,5				3,5		7
		Sum		3,5	3,5	3,5	3,5	3,5	3,5	21

Milestone 6 „Validationl“ (15.06.23)

Start	End	Task	Assigned to	Madeleine	Rajesh	Teja	Atif	Jannis	Manu
15.06.23	22.06.23
		Analise and Visualize Results	Teja			6				6
		Document Results	Manu					2	2
		Sum				6			2	8

22.06.23	29.06.23
		Prepare Presentation	Manu					5	5
		Final Version Documentation	Rajesh, Teja		3	3				6
		Print Documentation	Rajesh, Teja		0,5	0,5				1
		Sum			3,5	3,5			5	12

Milestone 7 „Experiments“ (29.06.23)
Start	End	Task	Assigned to	Madeleine	Rajesh	Teja	Atif	Jannis	Manu
29.06.23	06.07.23
		Prepare Presentation	Madeleine	5					5
		Sum		5	0	0	0	0	0	5

Milestone 8 „Final Report“ (06.07.23)

		Total Hours		57,5	41,5	40	38,5	46	43,5